## Instructions
Hours Budget Reconciliation — finding hours for out-of-scope work
When an unplanned deliverable lands (an ad-hoc interim, an extra TLF pack, a sponsor re-run) you have to answer one question: can we absorb this, or is it a change order? This workbook does the arithmetic; the 'FindHours playbook' HTML tells you where every number comes from. HOURS/EFFORT ONLY — no rates, no dollars, no headcount. Hours are what you control on a study and what a change order is written in.
The core idea (read this first)
Budget left is NOT what's left to spend. Planned − Actual looks like a cushion, but most of it is already committed to finishing work in flight. What you can actually redeploy is: NET FINDABLE = (Σ Planned + Contingency) − Σ EAC — total budget plus reserve, minus the honest forecast cost of finishing everything already in scope. Only that difference is real, spendable slack. The Effort Ledger computes it for you.
The four sheets
1) Instructions. 2) Effort Ledger: enter tasks in rows 3–17, plus contingency. These are synthetic examples. To add capacity, insert rows above TOTAL and extend formulas. 3) Find Hours: enter the new hours request. 4) Change Order: an example draft for review.
The workflow
1 | Get PLANNED hours from the project budget / SOW (a task grid by deliverable, often by role). One row per biometrics task on the Effort Ledger. Add the contingency / management reserve as its own row.
2 | Get ACTUAL hours from the time-tracking system, to a cutoff date. Correct for timesheet lag — add verbal estimates of worked-but-unlogged hours, or every task looks falsely under budget and your slack is a mirage.
3 | Enter EAC manually: the total hours expected at completion, at least the hours already worked. The workbook does not calculate EAC from % Complete; that column is optional context. Enter nonnegative Planned and Actual hours for every named task.
4 | Grade the slack. Only a REAL under-run is spendable: realized (completed task came in under) = safe; projected (in-progress, forecasting under, enough done to trust) = discount; illusory (early task, low actual only because it hasn't ramped) = NOT slack. Counting illusory slack is the #1 way this math goes wrong.
5 | Read NET FINDABLE off the ledger total. Be able to say which task each slack hour comes from and why the under-run is real, before you offer it to a PM.
6 | Enter a nonnegative hours request on Find Hours. Shortfall = MAX(0, Need − Net Findable), including any existing overall overrun. INPUT ERROR means a named task has missing/invalid hours, EAC is below Actual, % Complete is outside 0–100%, or contingency/request is invalid. Resolve inputs before using a verdict.
Estimating EAC — pick the method that fits what you know
• Actual + ETC (default): Actual-to-date + your honest estimate-to-complete of the remaining work. • % complete: EAC = Actual ÷ (% complete) — a task 60% done at 90 h forecasts ≈150 h; assumes effort tracks progress linearly. • Bottoms-up: Actual + a fresh estimate of each remaining item (e.g. 6 TLFs left × ~4 h). • Completed: EAC = Actual (task is done) — this is your realized variance. Variance = Planned − EAC: positive = forecasting under (possible slack); negative = forecasting over (a problem to raise, NOT a source of hours).
The find-hours decision tree (work the levers in this order)
1) Reallocate under-run SLACK to the new task — inside your project; you decide it and record which task gave / received. 2) Draw CONTINGENCY — a PM decision to record; once spent it's gone for the next surprise. 3) DEFER / re-sequence lower-priority in-scope work — trades schedule for hours; needs PM/sponsor to agree new dates. 4) CHANGE ORDER for any remaining shortfall — it's added scope; don't absorb it silently. Sequence: raise → lead biostat + PM review → sponsor signs → budget amended → THEN do the work.
How this connects to your real systems
• Planned hours come from the project budget / SOW task grid (kept by the PM or project finance, often in the CTMS or a planning workbook): read the biometrics task rows and their budgeted hours. • Actual hours come from the company timesheet system (hours logged to the project/task code): pull a report to a cutoff date, then add verbal estimates for worked-but-unlogged hours to correct for timesheet lag. • This workbook does not connect to those systems: you export from each and transcribe or paste the numbers here, then it computes net findable and the verdict. • The change order this workbook drafts routes through the real contract process (lead biostatistician + PM review, sponsor sign-off, SOW/budget amended), and the work is performed only after that. Everything stays in hours; pricing the effort is the PM's / finance's job, not this tool's.
100% synthetic. Hours/effort only — no dollars, rates, ROI, or headcount. Full worked detail + conversation scripts: the 'FindHours playbook' HTML next to this file.

## Effort Ledger
Effort Ledger (hours) — the rows below are a WORKED EXAMPLE; replace with your deliverables. Blue = you enter; grey = auto.
Deliverable | Planned Hours | Actual to Date | % Complete | EAC (est. at completion) | Variance (Planned-EAC) | Notes
SAP + randomization schedule | 80 | 78 | 100% | 78 | 2
ADaM specifications | 60 | 55 | 100% | 55 | 5
ADaM programming | 120 | 90 | 70% | 128 | -8
ADaM QC / validation | 80 | 40 | 60% | 70 | 10
TLF programming | 200 | 120 | 60% | 210 | -10
TLF QC (double-programming) | 120 | 50 | 45% | 110 | 10
PK / NCA (Phoenix) | 60 | 30 | 55% | 55 | 5
Interim / DSMB outputs | 40 | 40 | 100% | 40 | 0
CSR tables + narrative support | 90 | 10 | 10% | 85 | 5
TOTAL (deliverables) | 850 | 513 |  | 831 | 19
Contingency (management reserve, hrs) | 40
Net findable (incl. contingency) | 59

## Find Hours
Find Hours — where do the hours for a new deliverable come from?
New deliverable — estimated hours needed: | 45
Under-run slack (net) = Planned - EAC | 19
Contingency (management reserve) | 40
Net findable (total headroom) | 59
Shortfall (need - net findable, if positive) | 0
VERDICT | Absorbable internally - reallocate slack + contingency
Source the hours in this order:
1 · Reallocate under-run slack (already yours)
2 · Draw the contingency buffer (a recorded decision)
3 · Defer / re-sequence lower-priority in-scope work
4 · Change order for any remaining shortfall — don't absorb silently

## Change Order
Change Order — Effort (Hours) Request
Study / project
Change order #
Date raised
Raised by
The out-of-scope work (what & who asked)
Why it is out of scope
Estimated effort for the new work (hrs)
Found: under-run slack reallocated (hrs)
Found: contingency drawn (hrs)
Freed by deferring lower-priority work (hrs)
SHORTFALL requiring this change order (hrs)
Timeline / critical-path impact
Lead biostatistician (name / date)
Project manager (name / date)
Sponsor / accountable signer (name / date)