## Instructions
IRT / RTSM User Acceptance Testing — how to run this UAT (parallel-group study)
UAT is your confirmation, in a TEST environment, that the vendor's randomization & drug-supply build does exactly what the URS says — before a single real participant is randomized. This workbook is the tool you fill in as you go; the HTML 'UAT guide' walks the full detail with worked test scripts. As the biostatistician you OWN the confirmation that the IRT allocates per your list: right arm, right stratum, right block behavior, concealed until dosing.
The five sheets, in order of use
1) Instructions (this sheet). 2) Test Scripts — execute each test and fill the yellow columns. 3) Traceability — every URS requirement must map to ≥1 test (auto-flags gaps). 4) Defect Log — raise every failed test here. 5) Execution Summary — the go-live sign-off gate computes automatically. See also the 'Worked Example' sheet for two fully-filled test scripts.
Before you start — gather these inputs
• Approved URS (the contract of what the system must do). • Protocol (arms, ratio, stratification factors, block size, unblinding rules). • Randomization spec + a TEST randomization list loaded in the UAT environment (never the production list). • Drug-supply spec (kit types, visit-to-kit matrix, resupply thresholds, expiry). • UAT environment URLs + a test account for EACH role (investigator, unblinded pharmacist/statistician, blinded roles). • Test sites, test participant IDs, and the input values you'll use (weights for strata, visit dates).
The workflow
1 | Derive test cases from the URS. Each requirement → ≥1 positive test (does the right thing), ≥1 negative test (blocks the wrong thing), and a boundary test where a value sits on the edge of a rule (block edge, exact stratum cut-point, expiry today).
2 | Write each test so it is executable — a specific, verifiable expected result, not 'works correctly'. See the Worked Example sheet for the 6-part anatomy: precondition, test data, steps, expected, actual, evidence.
3 | Dry-run the scripts once yourself to catch bad test data / a not-ready environment. Fix the scripts, not the results.
4 | Execute formally. For each test fill: Actual, Status (Pass/Fail/Blocked/Not Run), Tester, Date — and capture a dated SCREENSHOT as evidence. 'Blocked' (environment not ready) is not a defect.
5 | Reconcile IRT allocations against the test list yourself — a sample across EVERY stratum, both arms of the ratio, and block boundaries. This is the biostatistician's job and the most common place IRT builds fail.
6 | Log every Fail on the Defect Log with a severity (see below); put the Defect ID back on the failed test row. Vendor fixes → you RETEST on the new build → REGRESSION-test anything the change could have touched. Record the build version.
7 | Close traceability: every URS requirement has an executed test (the Traceability sheet auto-flags any gap).
8 | When the gate reads READY, the UAT lead + accountable biostatistician SIGN the Execution Summary. File the whole package (plan, scripts, results+evidence, defect log, signed summary) to the eTMF.
Defect severity — drives whether it blocks go-live
CRITICAL — could compromise participant safety, break the blind, mis-randomize, mis-dose, or corrupt randomization/supply integrity (wrong stratum, duplicate rand number, expired kit dispensable, blinded role sees the arm). BLOCKS go-live.
MAJOR — significant functional error in a key workflow, not directly safety/integrity (resupply not triggering, wrong kit type for a visit, safety notification not sent). Blocks go-live until fixed.
MINOR — cosmetic / non-functional (notification subject omits site number, a label typo). Does not block; fix or waive with rationale.
The go-live gate (Execution Summary)
The gate flips from NOT ready to READY only when ALL THREE are true: (1) every Critical test is Pass; (2) zero OPEN Critical or Major defects; (3) 100% requirement traceability. The gate packages evidence — it does not grant approval. A named human still reviews and signs. In the delivered workbook the gate reads NOT ready because no tests are executed yet; it turns READY as you pass them.
How this connects to your real systems
• UAT runs in the IRT/RTSM vendor's staging environment (a separate instance from production), loaded with a TEST randomization list, never the production list. • You operate the vendor's system in a browser (register a test participant, randomize, dispense, trigger resupply, invoke emergency unblinding) and reconcile what it did against your list and specs. • This workbook is your independent record and sign-off, not a live connection: you transcribe Status, defects, and traceability here, with dated screenshots and system exports as the evidence. • The signed go-live summary (gate READY plus named human signatures) is what authorizes the vendor to promote the validated build to production; the whole package is filed to the eTMF.
100% synthetic test data. No PHI. 'Participant', not 'subject' (CDISC USUBJID/SUBJID preserved). Full worked detail: the 'UAT guide' HTML next to this file.

## Worked Example
Worked Example — what a good, executable test script looks like
Copy this shape into the Test Scripts sheet. The point: a specific, verifiable Expected result that a tester can objectively pass or fail — and, for randomization, a reconciliation you (the biostatistician) perform against the test list.
Field | Example A — RAND-02 (stratified allocation) | Example B — UNBL-01 (emergency unblinding)
Test ID / URS | RAND-02 · URS-RND-02 (allocate within entered stratum; factor = weight <70 / ≥70 kg; 2:1 active:placebo; block 6) | UNBL-01 · URS-UNB-01 (authorized role can break the blind for one participant; event is logged; participant is flagged)
Priority | Critical | Critical
Precondition | Test randomization list loaded in UAT; <70 kg stratum block 1 has an unused slot; you know the next expected list entry (as an authorized unblinded role). | A randomized test participant exists (e.g. 101-001); you are logged in with the unblinding-authorized role; the participant is not yet unblinded.
Test data | Participant 101-001, Site 101, screening weight 68.0 kg. | Participant 101-001; reason = 'medical emergency'.
Steps | 1. Log in as Investigator at Site 101. 2. Register 101-001; enter weight 68.0 kg. 3. Click Randomize. 4. Record the returned kit number + confirmation. 5. Log in as authorized unblinded statistician; open the allocation report for 101-001. | 1. Open 101-001. 2. Invoke emergency unblind; enter reason. 3. Confirm. 4. Check the audit trail and the participant's status. 5. Log in as a BLINDED role and confirm the arm is still not visible to them.
Expected result | 101-001 is allocated to the NEXT UNUSED entry in the <70 kg stratum, block 1 of the test list — matching arm, sequence, and kit number. The investigator confirmation shows a KIT ID only, not the arm. The allocation report row == the list row. | The treatment arm is revealed to the authorized role only. The unblinding is written to the audit trail (who, when, reason). The participant is flagged as unblinded. A BLINDED role still cannot see the arm. Any required safety notification fires.
How you verify | Put the test list next to the IRT allocation report; confirm cell-for-cell: stratum, block position, arm, kit number. Repeat across every stratum, both arms of the 2:1 ratio, and block boundaries — not one happy-path participant. | Inspect the audit-trail entry and the participant flag directly; confirm the blinded-role view is unchanged; confirm the notification was sent.
Actual (filled at run) | 101-001 → <70 kg, block 1, position 3, Arm A, kit K-1043. Confirmation showed kit K-1043 only. Report row == list row. ✔ | Arm revealed to unblinded role; audit entry present (user, timestamp, reason); participant flagged; blinded view unchanged; notification sent. ✔
Status / evidence | PASS — screenshot uat_rand02_2026-07-10.png attached. | PASS — screenshot uat_unbl01_2026-07-10.png + audit-trail export attached.
If it FAILED | Raise a Critical defect on the Defect Log (e.g. 'allocated from ≥70 kg list'), put the Defect ID on this test row, retest on the vendor's fix build, then regression-test all allocation tests. | Raise a Critical defect (e.g. 'blinded role can see arm after unblind' or 'no audit entry'), retest on the fix build, regression-test the unblinding + notification tests.

## Test Scripts
Test Scripts — execute each, then fill the yellow columns
Test ID | Area | URS Req | Priority | Test Title | Steps | Expected Result | Actual Result | Status | Tester | Date | Defect ID | Comments
RAND-01 | Randomization | URS-RND-01 | Critical | Allocation matches the approved schedule | Randomize test participants; export IRT allocation. | IRT allocation == approved randomization list (arm, kit, stratum) for all.
RAND-02 | Randomization | URS-RND-02 | Critical | Stratified allocation respects entered strata | Randomize across each stratification factor (e.g. site, factor). | Each participant allocated within the stratum entered.
RAND-03 | Randomization | URS-RND-03 | High | Allocation ratio honoured | Randomize a block; check active:control ratio (e.g. 2:1). | Realised ratio matches the protocol allocation ratio.
RAND-04 | Randomization | URS-RND-04 | High | Within-block balance / block integrity | Inspect allocation within each permuted block. | Within-block balance matches block size/ratio in the list.
RAND-05 | Randomization | URS-RND-05 | Critical | Unique randomization number | Two sites randomize concurrently. | Each participant gets a unique randomization number; no collision.
RAND-06 | Randomization | URS-RND-06 | Critical | Allocation concealment until dosing | View a participant as a blinded role before dosing. | Treatment concealed; blinded role sees a kit ID only.
RAND-07 | Randomization | URS-RND-07 | High | Reproducible from the frozen list | Reload the frozen list; re-run allocation. | Allocation is reproducible.
ENR-01 | Enrollment / screening | URS-ENR-01 | Medium | Unique screening numbers | Screen several participants. | Unique, sequential screening numbers.
ENR-02 | Enrollment / screening | URS-ENR-02 | High | Screen-fail cannot randomize | Mark a participant screen-fail; attempt to randomize. | Randomization blocked.
ENR-03 | Enrollment / screening | URS-ENR-03 | Medium | Re-screening permitted per protocol | Re-screen a permitted screen-fail. | Re-screening allowed with a new screening number.
ENR-04 | Enrollment / screening | URS-ENR-04 | High | Enrollment cap enforced | Enroll to the study cap + 1. | Enrollment blocked at the study cap.
DISP-01 | Drug dispensing | URS-DSP-01 | Critical | Dispensed kit matches allocated arm | Dispense at Day 1; compare kit to allocation. | Dispensed kit matches the allocated arm.
DISP-02 | Drug dispensing | URS-DSP-02 | High | Correct kit type per visit | Dispense across visits with differing kit types. | Correct kit type per visit per the supply matrix.
DISP-03 | Drug dispensing | URS-DSP-03 | Medium | Dispensing blocked outside visit window | Attempt dispensing outside the visit window. | Dispensing blocked / warned outside the window.
DISP-04 | Drug dispensing | URS-DSP-04 | High | Dispensing reconciles to dosing | Reconcile dispensing records to dosing. | Records reconcile to dosing events.
DISP-05 | Drug dispensing | URS-DSP-05 | Critical | Blinded kit labeling | Inspect kit label as a blinded role. | Label reveals no treatment arm; kit ID only.
SUP-01 | Resupply / inventory | URS-SUP-01 | High | Resupply triggered at threshold | Draw site stock below the resupply threshold. | Automatic resupply shipment triggered.
SUP-02 | Resupply / inventory | URS-SUP-02 | Critical | Expired kits not dispensable | Attempt to dispense an expired kit. | Expired kits are not dispensable.
SUP-03 | Resupply / inventory | URS-SUP-03 | High | Temperature-excursion kits quarantined | Flag a temperature excursion; attempt to dispense. | Excursion kits quarantined; not dispensable until released.
SUP-04 | Resupply / inventory | URS-SUP-04 | Medium | Inventory reconciliation | Reconcile IRT inventory to a physical count. | Inventory reconciles.
UNBL-01 | Emergency unblinding | URS-UNB-01 | Critical | Emergency unblind with audit trail | Perform an emergency unblind as an authorized role. | Treatment revealed; full audit trail (who/when/why).
UNBL-02 | Emergency unblinding | URS-UNB-02 | Critical | Unblinding role permissions | Attempt to unblind as an unauthorized role. | Unblinding denied for unauthorized roles.
UNBL-03 | Emergency unblinding | URS-UNB-03 | High | Post-unblind safety notification | After unblind, verify the safety notification. | Notification sent to the medical monitor / safety.
NOT-01 | Notifications / reports | URS-NOT-01 | Medium | Enrollment notification delivered | Randomize a participant; check enrollment notification. | Notification delivered to the distribution list.
NOT-02 | Notifications / reports | URS-NOT-02 | Medium | Low-stock alert delivered | Draw stock below threshold; check the alert. | Low-stock alert delivered to the CRA.
INT-01 | Data integration (EDC) | URS-INT-01 | High | IRT<->EDC participant reconciliation | Reconcile IRT participants against EDC. | IRT and EDC participant lists reconcile.
INT-02 | Data integration (EDC) | URS-INT-02 | High | Randomization data transfer to biostat | Transfer randomization data to biostatistics. | Export matches the IRT allocation (per role).

## Traceability
Requirement Traceability — every URS requirement needs a test
URS Req | Requirement description | # Tests (auto) | Covered (auto)
URS-DSP-01 | Dispensed kit matches allocated arm | 1 | Y
URS-DSP-02 | Correct kit type per visit | 1 | Y
URS-DSP-03 | Dispensing blocked outside visit window | 1 | Y
URS-DSP-04 | Dispensing reconciles to dosing | 1 | Y
URS-DSP-05 | Blinded kit labeling | 1 | Y
URS-ENR-01 | Unique screening numbers | 1 | Y
URS-ENR-02 | Screen-fail cannot randomize | 1 | Y
URS-ENR-03 | Re-screening permitted per protocol | 1 | Y
URS-ENR-04 | Enrollment cap enforced | 1 | Y
URS-INT-01 | IRT<->EDC participant reconciliation | 1 | Y
URS-INT-02 | Randomization data transfer to biostat | 1 | Y
URS-NOT-01 | Enrollment notification delivered | 1 | Y
URS-NOT-02 | Low-stock alert delivered | 1 | Y
URS-RND-01 | Allocation matches the approved schedule | 1 | Y
URS-RND-02 | Stratified allocation respects entered strata | 1 | Y
URS-RND-03 | Allocation ratio honoured | 1 | Y
URS-RND-04 | Within-block balance / block integrity | 1 | Y
URS-RND-05 | Unique randomization number | 1 | Y
URS-RND-06 | Allocation concealment until dosing | 1 | Y
URS-RND-07 | Reproducible from the frozen list | 1 | Y
URS-SUP-01 | Resupply triggered at threshold | 1 | Y
URS-SUP-02 | Expired kits not dispensable | 1 | Y
URS-SUP-03 | Temperature-excursion kits quarantined | 1 | Y
URS-SUP-04 | Inventory reconciliation | 1 | Y
URS-UNB-01 | Emergency unblind with audit trail | 1 | Y
URS-UNB-02 | Unblinding role permissions | 1 | Y
URS-UNB-03 | Post-unblind safety notification | 1 | Y

## Defect Log
Defect Log — raise every failed test here
Defect ID | Severity | Status | Found in Test | Description | Date Raised | Resolution

## Execution Summary
Execution Summary & Go-Live Sign-Off Gate
Execution
Total tests | 27
Passed | 0
Failed | 0
Blocked | 0
In Progress | 0
Not run | 27
Pass rate (of executed) | 0%
Go-live sign-off gate
Critical tests not yet passing | 9
Open Critical/Major defects | 0
Requirements without a test | 0
GO-LIVE GATE | NOT ready - blocked
Sign-off (when READY)
Tester — name
Tester — date
Biostatistician — name
Biostatistician — date
The gate packages the evidence; a named human signs. Deterministic criteria only.