# Early-Phase Clinical Pharmacology: Biostatistics Deliverables Pipeline

Protocol review → CSR draft · every document, dataset, and statistical output, with its owner, standard, and QC

Reference map, not a track record. This register maps the deliverables of a Phase 1 clinical pharmacology study and how each would be produced and checked. It is not a list of deliverables the author produced (the home page labels what he led or supported). A short appendix sets out where AI tools could assist under controls; it is a proposal, not an adopted policy.

Scope & how to read this. 132 deliverables across five stages of a Phase 1 clinical-pharmacology study (e.g., First-in-Human SAD/MAD with PK/PD, NCA + popPK, safety), each with its owner, inputs, outputs, governing standard, and QC method. The at-a-glance tables are below; the full register with every field is the companion `.xlsx`, and the one-page visual is the `.pdf` map. Standards as of October 2026: CDISC SDTMIG v3.4, ADaMIG v1.3, and Define-XML v2.1 (all FDA-required); ICH E3, E6(R3), E9(R1), and M11; systems designed to meet 21 CFR Part 11; ISPE GAMP 5.

## How the pipeline flows

Five sequential stages, each closed by a gate. A CDISC data-standards track (SDTM → ADaM → Define-XML + reviewer guides) runs through Stages 3 to 5, and a quality track (independent double programming, engine-of-record records, audit trail, named sign-off) runs across all five.

| Stage | Focus | Gate |
| --- | --- | --- |
| S1: Study Design & Protocol | Biostatistics shapes the design: estimands, endpoints, sample-size rationale, randomization, and the statistical sections of the protocol. | Protocol approved / finalized |
| S2: Planning & Specifications | Everything is specified before data: the SAP, TLF shells, ADaM/SDTM specs, the randomization schedule, the data-review and QC plans. | SAP & specifications final |
| S3: Data & CDISC | Raw data becomes standardized, conformant, traceable CDISC datasets (SDTM → ADaM) with reviewer guides and Define-XML, under full data integrity controls. | Database lock |
| S4: Analysis & QC | TLFs and PK/PD analyses are produced and independently double-programmed; reported numbers come from validated programs and engines (Phoenix WinNonlin or PKNCA for NCA). | All outputs QC-passed |
| S5: Reporting & CSR | Results become the CSR: statistical methods and results text, in-text tables/figures, appendices, the submission package, and cross-document consistency. | CSR draft delivered |

## S1: Study Design & Protocol

Biostatistics shapes the design: estimands, endpoints, sample-size rationale, randomization, and the statistical sections of the protocol.

| ID | Deliverable | Owner | Standard | QC |
| --- | --- | --- | --- | --- |
| S1-01 | Biostatistics input to protocol: design rationale & study design selection | Lead biostatistician | ICH M11 (CeSHarP protocol template) design section; ICH E9 (design principles, bias control); ICH E6(R3) GCP; FDA/EMA FIH guidance | Independent biostatistician peer review; cross-check design vs objectives/estimands; medical/clin-pharm/regulatory review; protocol team consensus |
| S1-02 | Objectives → estimands → endpoints alignment (ICH E9(R1) estimand framework) | Lead biostatistician | ICH E9(R1) estimand addendum; ICH E9; ICH M11 (estimand placement in protocol); ICH E3 | Independent biostatistician review of estimand completeness (all 5 attributes, every ICE addressed); clinical & clin-pharm alignment review; consistency check objectives↔estimands↔endpoints↔analysis sets |
| S1-03 | Statistical considerations / analysis-overview section of protocol | Lead biostatistician | ICH E9 / E9(R1); ICH M11 statistical-considerations section; ICH E3 (consistency with future CSR methods); ICH E6(R3) | Peer review by independent biostatistician; alignment check vs estimands and vs planned SAP scope; cross-functional protocol review |
| S1-04 | Analysis populations / analysis-set definitions (protocol-level) | Lead biostatistician | ICH E9 / E9(R1); ICH M11; CDISC ADaMIG v1.3 (population-flag conventions, e.g., SAFFL/PKFL); ICH E3 | Independent review of set definitions for mutual consistency and estimand linkage; clin-pharm review of PK-evaluable exclusion rules; traceability check to ADSL flag plan |
| S1-05 | Sample-size / power justification (or documented rationale for no formal sizing in FIH) | Lead biostatistician | ICH E9 (sample size & assumptions); ICH M11; FDA BA/BE & food-effect guidance; EMA bioequivalence/early-phase guidance; ICH E9(R1) (sizing tied to estimand) | Independent re-derivation/double-check of sample-size or precision calculation (independent code/program run); review of assumptions vs source data; documentation of method and seed/software version |
| S1-06 | Randomization design & specification (incl. sentinel dosing & active:placebo allocation) | Lead biostatistician | ICH E9 (randomization & blinding); ICH E6(R3) GCP; ICH M11; 21 CFR Part 11 (controlled, audit-trailed list generation); sponsor randomization SOP | Independent biostatistician review of design spec; verification that block/ratio/sentinel logic enforces intended allocation; segregation-of-duties check (spec author ≠ schedule generator); blinding-integrity review |
| S1-07 | DSMB/SRC/SEC charter: statistical decision rules & dose-escalation criteria | Lead biostatistician | ICH E9 (data monitoring, decision rules); ICH E6(R3) GCP; FDA guidance on Data Monitoring Committees; FIH guidance (escalation/stopping); ICH M11 | Independent review of decision-rule logic for unambiguity and safety conservatism; consistency check vs protocol dose levels and stopping rules; committee/regulatory review; (if model-based) operating-characteristics simulation review |
| S1-08 | Dose-escalation operating-characteristics simulation (design-stage) | Lead biostatistician | ICH E9 / E9(R1); FDA adaptive-design & FIH guidance; reproducibility per 21 CFR Part 11 (versioned, seeded code); sponsor simulation SOP | Independent re-run/replication of simulation with documented seed & environment; code review; scenario-grid completeness review; sanity-check of OC against design intuition |
| S1-09 | Interim / adaptive-design elements specification (if any) | Lead biostatistician | ICH E9 / E9(R1); FDA Adaptive Designs for Clinical Trials guidance; EMA reflection paper on adaptive designs; ICH M11; 21 CFR Part 11 | Independent statistical review of adaptation rules & error-rate control; simulation of operating characteristics; firewall/independence review; documentation of 'N/A' decision where no adaptation |
| S1-10 | PK precision / variability assumptions memo (CV%, BLQ/LLOQ & sampling-scheme adequacy) | Lead biostatistician | ICH E9; FDA/EMA PK and BA/BE guidance; sponsor NCA/PK SOP; reproducible assumptions | Joint biostatistician–PK scientist review; cross-check sampling adequacy vs predicted t1/2; sensitivity of precision to CV% assumptions; documentation of assumption sources |
| S1-11 | Biostatistician protocol review & sign-off | Lead biostatistician | ICH E9 / E9(R1); ICH M11; ICH E6(R3) GCP; 21 CFR Part 11 (electronic signature & audit trail); sponsor protocol-approval SOP | Comment-tracking & resolution log; independent (second-biostatistician) consistency check on objectives↔estimands↔endpoints; signed/audited approval; amendment version control |
| S1-12 | Emergency unblinding / code-break plan (design-stage definition) | Lead biostatistician | ICH E6(R3) GCP; ICH E9 (blinding integrity); 21 CFR Part 11 (audit trail of unblinding); pharmacovigilance regs; sponsor unblinding SOP | Independent review of firewall & segregation-of-duties; verification unblinding pathway is auditable and minimally disruptive to the blind; cross-check vs DSMB charter and randomization spec |
| S1-13 | Blinded Sample-Size Re-Estimation (BSSR) Plan: design-stage provision | Lead biostatistician | ICH E9 / E9(R1); ICH E6(R3) GCP | Biostatistician review and sign-off; no unblinded data touched |
| S1-14 | Estimand-to-design traceability & assumptions log (intercurrent-event strategy register) | Lead biostatistician | ICH E9(R1) estimand framework | Biostatistician + medical reviewer sign-off |

Stage gate: Protocol approved / finalized. 14 deliverables.

## S2: Planning & Specifications

Everything is specified before data: the SAP, TLF shells, ADaM/SDTM specs, the randomization schedule, the data-review and QC plans.

| ID | Deliverable | Owner | Standard | QC |
| --- | --- | --- | --- | --- |
| S2-01 | Statistical Analysis Plan (SAP) | Lead biostatistician | ICH E9 + E9(R1) estimands, ICH E3 (alignment with CSR), ICH E6(R3) GCP, ICH M11; version-controlled, dated, signed | Senior biostatistician peer review; cross-check vs protocol & estimands; documented sign-off; formal version control of amendments |
| S2-02 | SAP Amendment & Version-Control Log | Lead biostatistician | ICH E9, ICH E3, ICH E6(R3), 21 CFR Part 11 (audit trail), ALCOA++ | Independent review of each change; timestamp vs lock/unblinding verified; Part 11 audit trail retained |
| S2-03 | Analysis-Set / Population Definitions | Lead biostatistician | ADaMIG v1.3 (population flags), ICH E9(R1), CDISC CT | Independent reviewer confirms flag logic vs SAP; double-programmed in ADSL; reconciled at blinded data review |
| S2-04 | TLF Shells / Mock-Up Shells (Tables, Listings, Figures) | Lead biostatistician | ICH E3 (in-text/appendix structure), sponsor output standards, CDISC CT for terminology | Peer/medical-writer/clinical review of shells; titles/footnotes vs SAP; dummy-data render test for layout |
| S2-05 | TLF Inventory / Table of Contents | Lead biostatistician | ICH E3, sponsor standards | Cross-check vs SAP analyses (no orphan/missing outputs); peer review |
| S2-06 | ADaM Dataset Specifications (ADSL) | Stat programmer | ADaMIG v1.3, CDISC CT, Define-XML v2.1, traceability to SDTM | Spec peer review; downstream independent double-programming of ADSL; Pinnacle 21 ADaM conformance |
| S2-07 | ADaM Dataset Specification (ADPC: PK Concentrations) | Stat programmer | ADaMIG v1.3, CDISC CT, Define-XML v2.1, ICH PK reporting practice | Spec review vs PK plan (BLQ/time rules); independent double-programming of ADPC; reconciliation to SDTM PC |
| S2-08 | ADaM Dataset Specification (ADPP: PK Parameters) | Stat programmer | ADaMIG v1.3, CDISC CT (PK parameters), Define-XML v2.1 | Spec review vs parameter list; ADPP reconciled to validated Phoenix output; independent double-programming of structure |
| S2-09 | ADaM Dataset Specification (ADAE: Adverse Events) | Stat programmer | ADaMIG v1.3 (OCCDS), MedDRA, CDISC CT, Define-XML v2.1 | Spec review of TEAE logic; independent double-programming; reconcile vs SDTM AE |
| S2-10 | ADaM Dataset Specifications (ADLB / ADVS / ADEG: Labs, Vitals, ECG) | Stat programmer | ADaMIG v1.3, CDISC CT, Define-XML v2.1 | Spec review of baseline/window/unit logic; independent double-programming; SDTM reconciliation |
| S2-11 | ADaM Dataset Specification (ADPD: Pharmacodynamics) | Stat programmer | ADaMIG v1.3, CDISC CT, Define-XML v2.1 | Spec review vs PD plan; independent double-programming; SDTM reconciliation |
| S2-12 | SDTM Mapping Specification | Stat programmer | CDISC SDTMIG v3.4, Controlled Terminology, Define-XML v2.1 | Independent review vs SDTMIG/CT; Pinnacle 21 rule mapping; traceability check raw->SDTM |
| S2-13 | Annotated CRF (aCRF): Preparation & Review | Stat programmer | CDISC SDTMIG v3.4, Define-XML v2.1, CDISC aCRF conventions | Page-by-page review vs mapping spec; consistency with Define-XML origin; peer review |
| S2-14 | Programming Specifications / Derivation Specs | Stat programmer | ADaMIG v1.3, Define-XML v2.1 (value-level), CDISC CT | Independent spec review; basis for double-programming reconciliation; traceability to SAP |
| S2-15 | PK Analysis Plan (NCA detail) | PK scientist | ICH PK reporting practice, regulatory NCA guidance, Phoenix WinNonlin (validated NCA engine) | PK scientist + biostatistician review; rules cross-checked vs SAP; Phoenix template qualified |
| S2-16 | popPK / Exposure-Response Modeling Analysis Plan (PMAP) | Pharmacometrician | Regulatory popPK/E-R guidance, ICH E9(R1), software validation; NONMEM/Monolix as analysis engines | Independent pharmacometrics review; model-qualification criteria pre-specified; run records reproducible |
| S2-17 | NONMEM/Monolix Analysis Dataset Specification (PK/PD modeling dataset) | Pharmacometrician | popPK dataset conventions, traceability to ADaM, software validation | Independent check vs ADaM source; structure/covariate completeness verified; reproducibility |
| S2-18 | Randomization Schedule Generation | Lead biostatistician | ICH E6(R3), ICH E9, 21 CFR Part 11 (audit trail, access control), ALCOA++ | Independent QC of allocation vs spec (ratios/blocks/strata); seed/reproducibility verified; secured storage |
| S2-19 | Randomization Specification | Lead biostatistician | ICH E6(R3), ICH E9, 21 CFR Part 11 | Independent review vs protocol; IRT UAT alignment; documented approval |
| S2-20 | Unblinding / Code-Break Plan | Lead biostatistician | ICH E6(R3), ICH E9, 21 CFR Part 11 (audit trail), ALCOA++ | SOP/charter alignment review; role/firewall verification; emergency-unblinding log tested |
| S2-21 | Data Review Plan / Blinded Data-Review Plan | Lead biostatistician | ICH E9 (pre-unblinding decisions), ICH E6(R3), ALCOA++ | Peer review; decisions recorded with timestamp before unblinding; consistency with SAP |
| S2-22 | Define-XML Planning / Metadata Strategy | Stat programmer | Define-XML v2.1, CDISC SDTMIG v3.4 / ADaMIG v1.3, Controlled Terminology | Metadata completeness vs specs; Pinnacle 21 define checks; value-level metadata review |
| S2-23 | Controlled Terminology Plan / CT Version Pinning | Stat programmer | CDISC Controlled Terminology, SDTMIG v3.4, ADaMIG v1.3, Define-XML v2.1 | Version-pin verification; Pinnacle 21 CT checks; extensible-codelist review |
| S2-24 | Validation / QC Plan (Independent Double-Programming Strategy) | Lead biostatistician | ICH E6(R3), 21 CFR Part 11, ALCOA++, CDISC conformance; sponsor validation SOPs | Risk-based assignment reviewed/approved; double-programming mandatory for key outputs; audit-ready |
| S2-25 | Pseudo / Dummy Data for Shell Testing | Stat programmer | CDISC structures (for realism), sponsor standards; non-PHI by construction | Structure conformance to ADaM specs; coverage of edge cases (BLQ, missing, windows) |
| S2-26 | Data-Transfer Specifications (DTS / interface review) | Data mgmt | CDISC SDTMIG v3.4 (target), 21 CFR Part 11, ALCOA++, sponsor DM SOPs | Test-transfer review; key/format/unit verification; reconciliation procedure agreed |
| S2-27 | Dose-Escalation / Operating-Characteristics Simulation Plan & Outputs | Lead biostatistician | ICH E9 + E9(R1), reproducibility/software validation | Independent review of assumptions/code; seed/reproducibility documented; results sanity-checked |
| S2-28 | Interim Analysis Plan / DSMB statistical output specifications & firewall (SAP-level) | Independent unblinded statistician + lead biostatistician | ICH E9; ICH E6(R3); FDA/EMA DSMB guidance | Independent unblinded statistician; firewall enforced |
| S2-29 | Bioanalytical data-transfer & PK sample reconciliation specification (LC-MS/MS lab interface) | PK scientist + biostat programming + bioanalytical lab | CDISC SDTMIG PC domain; FDA Bioanalytical Method Validation guidance; ALCOA++ | Double-check vs lab dictionary; PK scientist sign-off |
| S2-30 | Value-Level Metadata (VLM) specification for Define-XML | Biostat programming / metadata lead | Define-XML v2.1; CDISC ADaMIG v1.3 / SDTMIG v3.4 | Independent review vs datasets; Pinnacle 21 Define validation |
| S2-31 | Software / computing environment validation & installation qualification (IQ/OQ) records | Biometrics systems / QA + statistical programming | 21 CFR Part 11; GAMP 5; ICH E6(R3) | QA review; reported numbers always from validated engines |

Stage gate: SAP & specifications final. 31 deliverables.

## S3: Data & CDISC

Raw data becomes standardized, conformant, traceable CDISC datasets (SDTM → ADaM) with reviewer guides and Define-XML, under full data integrity controls.

| ID | Deliverable | Owner | Standard | QC |
| --- | --- | --- | --- | --- |
| S3-01 | EDC / raw data extracts & Data Transfer Agreement (DTA) interface | Data mgmt (biostat/stat programmer co-reviewer) | 21 CFR Part 11, ALCOA++, ICH E6(R3); CDISC CT for code lists; sponsor DTA SOP | Transfer-spec conformance check on each load; record counts & checksum reconciliation; test-transfer (dry-run) before first production transfer |
| S3-02 | Biostat review of edit checks / data queries / data-review listings | Lead biostatistician / Stat programmer (with Data mgmt) | ICH E6(R3) GCP, 21 CFR Part 11, ALCOA++; Data Review Plan | Independent review of listing logic; query resolution tracked to closure; reconciliation against SAP-defined critical variables |
| S3-03 | Annotated CRF (aCRF) | Stat programmer (CDISC/SDTM lead) | CDISC SDTMIG v3.4, Define-XML v2.1, Controlled Terminology; CDISC aCRF conventions | Peer review against final CRF and SDTM specs; Pinnacle 21 / Define linkage check that every annotated origin resolves |
| S3-04 | SDTM datasets: DM (Demographics) | Stat programmer (CDISC/SDTM lead) | CDISC SDTMIG v3.4, Controlled Terminology, Define-XML v2.1 | Independent double-programming + Pinnacle 21 conformance; reconciliation to raw and randomization |
| S3-05 | SDTM datasets: PC (Pharmacokinetic Concentrations) | Stat programmer (CDISC/SDTM lead) with PK scientist | CDISC SDTMIG v3.4 (Findings), Define-XML v2.1, value-level metadata; CT for units/analytes | Independent double-programming + Pinnacle 21; 100% reconciliation to bioanalytical transfer (record count, value, BLQ flags); nominal-vs-actual time check |
| S3-06 | SDTM datasets: PP (Pharmacokinetic Parameters) | Stat programmer (CDISC/SDTM lead) with PK scientist | CDISC SDTMIG v3.4 (PP domain), CT for PK parameters (PKPARMCD), Define-XML v2.1, RELREC linkage to PC | Reconciliation to Phoenix output (the engine of record); independent double-programming of the SDTM structure; Pinnacle 21 |
| S3-07 | SDTM datasets: EX (Exposure) | Stat programmer (CDISC/SDTM lead) | CDISC SDTMIG v3.4 (Interventions), Define-XML v2.1, Controlled Terminology | Independent double-programming + Pinnacle 21; reconciliation to randomization and to PC time-after-dose derivation |
| S3-08 | SDTM datasets: AE (Adverse Events) | Stat programmer (CDISC/SDTM lead) with Data mgmt (MedDRA coding) | CDISC SDTMIG v3.4 (Events), MedDRA (versioned), Define-XML v2.1, CT | Independent double-programming + Pinnacle 21; MedDRA coding QC; reconciliation to safety database/SAE recon |
| S3-09 | SDTM datasets: LB (Laboratory) | Stat programmer (CDISC/SDTM lead) | CDISC SDTMIG v3.4 (Findings), CT/LOINC, Define-XML v2.1 value-level metadata, unit standardization | Independent double-programming + Pinnacle 21; 100% reconciliation to lab transfer; unit conversion QC |
| S3-10 | SDTM datasets: VS (Vital Signs) | Stat programmer (CDISC/SDTM lead) | CDISC SDTMIG v3.4 (Findings), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; reconciliation to raw |
| S3-11 | SDTM datasets: EG (ECG) | Stat programmer (CDISC/SDTM lead) with PK/cardiac-safety scientist | CDISC SDTMIG v3.4 (Findings), CT, Define-XML v2.1; time-matched to PC for C-QTc | Independent double-programming + Pinnacle 21; reconciliation to ECG core-lab transfer; PK time-matching QC |
| S3-12 | SDTM datasets: DS (Disposition) | Stat programmer (CDISC/SDTM lead) | CDISC SDTMIG v3.4 (Events), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; reconciliation to enrollment/randomization counts |
| S3-13 | SDTM datasets: MH (Medical History) | Stat programmer (CDISC/SDTM lead) with Data mgmt (coding) | CDISC SDTMIG v3.4 (Events), MedDRA, CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; coding QC |
| S3-14 | SDTM datasets: CM (Concomitant/Prior Medications) | Stat programmer (CDISC/SDTM lead) with Data mgmt (WHODrug coding) | CDISC SDTMIG v3.4 (Interventions), WHODrug (versioned), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; coding QC |
| S3-15 | SDTM datasets: PD/DV and other supporting domains (PD/PE/SU/QS, DV, CO, SE/TA/TV/TE trial design, SUPPQUAL, RELREC) | Stat programmer (CDISC/SDTM lead) with PD/PK scientists | CDISC SDTMIG v3.4 (Findings/Events/Special-Purpose/Trial-Design/SUPP/RELREC), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; RELREC integrity check (PC<->PP); deviation-classification reconciliation |
| S3-16 | SDTM Define-XML (define.xml + stylesheet) | Stat programmer (CDISC/SDTM lead) | CDISC Define-XML v2.1, SDTMIG v3.4, Controlled Terminology | Pinnacle 21 Define conformance + dataset-define consistency; peer review; origin/aCRF cross-link check |
| S3-17 | SDTM Reviewer Guide (cSDRG) | Stat programmer (CDISC/SDTM lead) / Lead biostatistician | PHUSE cSDRG template, CDISC SDTMIG v3.4, Define-XML v2.1 | Peer review; consistency with Define-XML and Pinnacle 21 explanations; sign-off |
| S3-18 | ADaM datasets: ADSL (participant-level analysis dataset) | Stat programmer (ADaM lead) / Lead biostatistician | CDISC ADaMIG v1.3, Define-XML v2.1, traceability to SDTM, CT | Independent double-programming + Pinnacle 21 ADaM checks; population-flag reconciliation to disposition/randomization |
| S3-19 | ADaM datasets: ADPC (PK Concentrations Analysis) | Stat programmer (ADaM lead) with PK scientist | CDISC ADaMIG v1.3 (BDS / PK ADaM), Define-XML v2.1, traceability to PC/EX, CT | Independent double-programming + Pinnacle 21; time-after-dose & BLQ-rule QC; reconciliation to PC |
| S3-20 | ADaM datasets: ADPP (PK Parameters Analysis) | Stat programmer (ADaM lead) with PK scientist | CDISC ADaMIG v1.3, Define-XML v2.1, traceability to PP/Phoenix, CT (PK params) | Reconciliation to Phoenix (engine of record); independent double-programming; Pinnacle 21 |
| S3-21 | ADaM datasets: ADAE (Adverse Events Analysis) | Stat programmer (ADaM lead) / Lead biostatistician | CDISC ADaMIG v1.3 OCCDS, MedDRA, Define-XML v2.1, traceability to AE, CT | Independent double-programming + Pinnacle 21; TRTEMFL logic QC; reconciliation to SDTM AE & SAE database |
| S3-22 | ADaM datasets: ADLB (Laboratory Analysis) | Stat programmer (ADaM lead) | CDISC ADaMIG v1.3 BDS, Define-XML v2.1 value-level metadata, traceability to LB, CT | Independent double-programming + Pinnacle 21; baseline/change & category-derivation QC; reconciliation to LB |
| S3-23 | ADaM datasets: ADVS (Vital Signs Analysis) | Stat programmer (ADaM lead) | CDISC ADaMIG v1.3 BDS, Define-XML v2.1, traceability to VS, CT | Independent double-programming + Pinnacle 21; baseline/change QC; reconciliation to VS |
| S3-24 | ADaM datasets: ADEG (ECG Analysis) | Stat programmer (ADaM lead) with cardiac-safety/PK scientist | CDISC ADaMIG v1.3 BDS, Define-XML v2.1, traceability to EG/PC, CT; ICH E14/concentration-QTc practice | Independent double-programming + Pinnacle 21; QTc category & time-matching QC; reconciliation to EG |
| S3-25 | ADaM datasets: ADPD and other analysis datasets (ADPD, ADCM, ADMH, deviation/exposure analysis as applicable) | Stat programmer (ADaM lead) with PD/PK scientists | CDISC ADaMIG v1.3 BDS/OCCDS, Define-XML v2.1, traceability to SDTM, CT | Independent double-programming + Pinnacle 21; PK-PD linkage & baseline/change QC |
| S3-26 | ADaM Define-XML (define.xml + stylesheet) | Stat programmer (ADaM lead) | CDISC Define-XML v2.1, ADaMIG v1.3, Controlled Terminology | Pinnacle 21 Define conformance + dataset-define consistency; derivation-method review; traceability check |
| S3-27 | ADaM Reviewer Guide (ADRG) | Stat programmer (ADaM lead) / Lead biostatistician | PHUSE ADRG template, CDISC ADaMIG v1.3, Define-XML v2.1 | Peer review; consistency with Define-XML, SAP and Pinnacle 21 explanations; sign-off |
| S3-28 | CDISC conformance / validation (Pinnacle 21) report: SDTM & ADaM | Stat programmer (CDISC lead) / Lead biostatistician | CDISC conformance rules, SDTMIG v3.4, ADaMIG v1.3, Define-XML v2.1, FDA/PMDA validator rules | Validated Pinnacle 21 engine; documented triage/disposition of every finding; reviewer-guide reconciliation |
| S3-29 | PK bioanalytical sample reconciliation (concentration data load & BLQ handling) | PK scientist / Stat programmer (with bioanalytical lab & Data mgmt) | FDA/ICH M10 bioanalytical method validation, 21 CFR Part 11, ALCOA++; PK analysis plan BLQ rules | 100% sample-accountability reconciliation; independent check of BLQ/LLOQ flagging; record-count/value match to transfer |
| S3-30 | Blinded data review outputs (data-review listings & blinded review meeting package) | Lead biostatistician (with Data mgmt, Clinical, PK) | ICH E9/E9(R1), ICH E6(R3); Data Review Plan; 21 CFR Part 11 | Independent review of listings; documented blinded decisions (minutes) prior to unblinding; reconciliation to SAP rules |
| S3-31 | Dry-run / test datasets & dry-run TLF execution | Stat programmer / Lead biostatistician | Sponsor validation/QC plan; CDISC SDTMIG v3.4/ADaMIG v1.3; 21 CFR Part 11 (program version control) | Independent double-programming on dry-run; shell-vs-output reconciliation; defect tracking to closure |
| S3-32 | Data cleaning / soft lock | Data mgmt (with Lead biostatistician sign-off) | ICH E6(R3), 21 CFR Part 11, ALCOA++; sponsor lock SOP | Lock checklist completion; cross-functional reconciliation sign-off; audit-trail review |
| S3-33 | Database hard lock | Data mgmt (cross-functional sign-off incl. Lead biostatistician) | ICH E6(R3), 21 CFR Part 11 (audit trail/e-records), ALCOA++; sponsor lock SOP | Formal hard-lock checklist & multi-party sign-off; audit-trail/lock verification; snapshot integrity check |
| S3-34 | Traceability (raw -> SDTM -> ADaM) matrix | Stat programmer (CDISC lead) / Lead biostatistician | CDISC SDTMIG v3.4/ADaMIG v1.3/Define-XML v2.1 traceability principles; ICH E6(R3), ALCOA++ | Cross-link verification raw<->SDTM<->ADaM; peer review; consistency with define/reviewer guides |
| S3-35 | Controlled Terminology & coding-dictionary version management (CDISC CT, MedDRA, WHODrug) | Data mgmt / Stat programmer (CDISC lead) | CDISC Controlled Terminology (versioned), MedDRA, WHODrug; Define-XML v2.1; 21 CFR Part 11 | Version-lock verification; CT-conformance via Pinnacle 21; coding QC against locked dictionaries |
| S3-36 | Randomization QC / verification report (schedule vs IXRS/EDC reconciliation) | Independent statistician (not the schedule generator) | ICH E6(R3); 21 CFR Part 11; ALCOA++ | Independent double-check; segregation of duties from generator |
| S3-37 | Emergency unblinding / code-break event log & reconciliation | Unblinded pharmacovigilance / IXRS admin + biostat | ICH E6(R3); 21 CFR Part 11 audit trail | Independent verification; segregation from blinded team |
| S3-38 | Protocol-deviation classification & reconciliation log (important vs non-important) | Clinical ops + biostat (blinded review) | ICH E3; ICH E6(R3); ICH E9(R1) (impact on populations/estimands) | Blinded review meeting; medical/biostat adjudication documented |
| S3-39 | Analysis-population derivation & participant-disposition reconciliation (population-flag QC) | Lead biostatistician + programming | CDISC ADaMIG v1.3 (ADSL population flags); ICH E9(R1) | Independent double-programming + blinded allocation sign-off |
| S3-40 | Data Review Meeting minutes & blinded data-review sign-off (pre-lock) | Cross-functional (DM, biostat, clinical, PK), blinded | ICH E6(R3); ALCOA++; 21 CFR Part 11 | Attendees confirm minutes; signatures retained |
| S3-41 | Database lock authorization & 21 CFR Part 11 audit-trail review / system records | Data management + QA + biostat | 21 CFR Part 11; ALCOA++; ICH E6(R3) | QA review of audit trail; independent lock approval |
| S3-42 | PK sampling-time deviation & actual-vs-nominal time reconciliation (PK timing dataset QC) | PK scientist + biostat programming | CDISC PC/PP domains; FDA PK guidance; ALCOA++ | Independent check vs source; PK scientist sign-off |

Stage gate: Database lock. 42 deliverables.

## S4: Analysis & QC

TLFs and PK/PD analyses are produced and independently double-programmed; reported numbers come from validated programs and engines (Phoenix WinNonlin or PKNCA for NCA).

| ID | Deliverable | Owner | Standard | QC |
| --- | --- | --- | --- | --- |
| S4-01 | Analysis environment qualification & program setup (folder structure, validated software versions, run/seed control) | Stat programmer | 21 CFR Part 11; ALCOA++; ICH E6(R3) (computerized systems / software validation); CSV/IQ-OQ-PQ | Installation/operational qualification records; environment qualification checklist; version log; reviewer sign-off |
| S4-02 | Disposition tables (screening, randomization, dosed, completed/discontinued; analysis-set attribution) | Stat programmer | ICH E3; ADaMIG v1.3 (ADSL); SAP | Independent double-programming + reconciliation against shells; population counts cross-checked to ADSL |
| S4-03 | Demographics & baseline characteristics tables | Stat programmer | ICH E3; ADaMIG v1.3; CDISC CT; SAP | Independent double-programming + reconciliation; descriptive stats verified against ADSL/raw |
| S4-04 | Exposure / dosing & treatment-compliance tables | Stat programmer | ICH E3; SDTMIG v3.4 (EX); ADaMIG v1.3; SAP | Independent double-programming + reconciliation; dosing records cross-checked to EX/EC |
| S4-05 | Protocol-deviation summary tables (with importance classification) | Stat programmer | ICH E3; ICH E6(R3); SDTMIG v3.4 (DV); SAP | Independent double-programming + reconciliation; classification reviewed at blinded data review |
| S4-06 | PK concentration summary tables + mean concentration-time figures (linear & semi-log) | Stat programmer | ICH E3; ADaMIG v1.3 (ADPC); SDTMIG v3.4 (PC); SAP / PK analysis plan | Independent double-programming + reconciliation; BLQ handling verified; figures QC'd vs tables |
| S4-07 | NCA execution in validated Phoenix WinNonlin (PK parameter derivation) | PK scientist | Validated NCA in Phoenix WinNonlin; ICH E3; ADaMIG v1.3 (ADPP); SAP / PK analysis plan | Phoenix is the validated engine of record; independent re-derivation of key parameters (second analyst / second tool) + reconciliation; lambda_z selection reviewed; run records archived |
| S4-08 | PK parameter (NCA) summary tables (Cmax, Tmax, AUC, t1/2, CL/F, Vz/F) | Stat programmer | ICH E3; ADaMIG v1.3 (ADPP); SAP | Independent double-programming of the summary table + reconciliation; values traceable to validated Phoenix ADPP |
| S4-09 | Dose-proportionality & accumulation analyses | Stat programmer | ICH E3; SAP / PK analysis plan; relevant FDA/EMA dose-proportionality guidance | Independent double-programming + reconciliation; model specification reviewed; outputs traced to validated ADPP |
| S4-10 | Food-effect / DDI / relative BA-BE statistical analysis (ANOVA, 90% CI, GMR), if applicable | Stat programmer | ICH E3; FDA/EMA BE & food-effect & DDI guidances; SAP | Independent double-programming of mixed-model/GMR/90% CI + reconciliation; model statement (fixed/random effects) reviewed; values traced to validated ADPP |
| S4-11 | Concentration-QTc (C-QTc) / QT-QTc analysis, if applicable | Pharmacometrician | ICH E14 + E14 Q&A (R3) (Q5.1, concentration-response modeling) and E14/S7B Q&As (2022); ICH E3; ADaMIG v1.3 (ADEG); SAP | Independent re-modeling / double-programming + reconciliation; C-QTc model assumptions reviewed; run records archived |
| S4-12 | popPK / exposure-response modeling (NONMEM/Monolix) with run records | Pharmacometrician | Validated NONMEM/Monolix; popPK analysis plan; FDA/EMA popPK & exposure-response guidance; ICH E3 | Run records (control streams/seeds/logs) archived; independent review of model code & assumptions; key results reproduced; VPC/GOF reviewed |
| S4-13 | Safety TLFs: TEAEs (overview, by SOC/PT, severity, relationship, by dose) | Stat programmer | ICH E3; MedDRA; ADaMIG v1.3 (ADAE); SAP | Independent double-programming + reconciliation; TEAE flag/derivation verified; counts cross-checked to ADAE |
| S4-14 | Safety TLFs: deaths, SAEs, and AEs leading to discontinuation | Stat programmer | ICH E3; ICH E2A/E6(R3); MedDRA; SAP | Independent double-programming + reconciliation; SAE/death flags reconciled with safety database/PV |
| S4-15 | Safety TLFs: clinical laboratory analyses (summary, change-from-baseline, shift tables, outliers, Hy's law) | Stat programmer | ICH E3; CDISC CT; ADaMIG v1.3 (ADLB); SAP | Independent double-programming + reconciliation; reference-range/grade derivations verified |
| S4-16 | Safety TLFs: vital signs, ECG (12-lead parameters), physical exam | Stat programmer | ICH E3; ICH E14 (ECG categorical); ADaMIG v1.3 (ADVS/ADEG); SAP | Independent double-programming + reconciliation; baseline/CFB and outlier criteria verified |
| S4-17 | PD endpoint analyses (biomarker / target-engagement summaries and PK/PD) | Pharmacometrician | ICH E3; ADaMIG v1.3 (ADPD); SAP | Independent double-programming + reconciliation; derivations/units verified; PK/PD models reviewed |
| S4-18 | Immunogenicity / anti-drug antibody (ADA) analyses, if applicable | Stat programmer | ICH E3; FDA/EMA immunogenicity guidance; CDISC IS; SAP | Independent double-programming + reconciliation; TE-ADA derivation verified |
| S4-19 | Exploratory / post-hoc analyses | Lead biostatistician | ICH E3; ICH E9; SAP (exploratory designation) | Risk-based QC (key exploratory outputs double-programmed); exploratory flagging reviewed |
| S4-20 | Statistical analysis execution (run-all production of SAP-specified analyses) | Stat programmer | ICH E9; ICH E3; 21 CFR Part 11; ALCOA++; SAP | Log review (no errors/warnings); output-vs-shell check; independent double-programming reconciliation gate before release |
| S4-21 | Independent double-programming QC + reconciliation (discrepancy resolution) | Stat programmer | ICH E6(R3); 21 CFR Part 11; ALCOA++; validation/QC plan; SAP | This IS the QC step: independent double-programming + documented reconciliation; lead biostatistician sign-off |
| S4-22 | TLF validation / QC documentation & discrepancy log | Stat programmer | 21 CFR Part 11; ALCOA++; ICH E6(R3); validation/QC plan | Completeness/consistency review of QC records; lead biostatistician sign-off |
| S4-23 | Blinded / blind data-review meeting & documented decisions | Lead biostatistician | ICH E9; ICH E6(R3); ICH E3; SAP / Data Review Plan | Decisions documented before unblinding; cross-functional sign-off; decisions locked |
| S4-24 | Unblinding / code-break execution | Lead biostatistician | ICH E6(R3); 21 CFR Part 11 (audit trail/access); unblinding/code-break SOP | Authorization & timing documented; access-controlled execution; audit trail; segregation of duties verified |
| S4-25 | Pharmacometrics / popPK analysis report | Pharmacometrician | FDA/EMA popPK & exposure-response guidance; ICH E3; modeling analysis plan | Independent review of model & report; key results reproduced; run-record completeness check |
| S4-26 | QC documentation / validation records package (analysis stage) | Lead biostatistician | 21 CFR Part 11; ALCOA++; ICH E6(R3); validation/QC plan | Completeness/traceability review; lead biostatistician sign-off; archived per retention policy |
| S4-27 | Phoenix WinNonlin NCA parameter-derivation QC / independent NCA verification record | PK scientist + independent PK QC reviewer | Phoenix WinNonlin (validated NCA); FDA PK guidance; 21 CFR Part 11 | Independent PK reviewer; documented parameter verification |
| S4-28 | Pharmacometrics model qualification & validation records (covariate selection, GOF, VPC, bootstrap, run log) | Pharmacometrician + independent reviewer | NONMEM/Monolix; FDA popPK guidance; 21 CFR Part 11 | Independent pharmacometrics review; reproducible run records |
| S4-29 | Risk-based QC plan execution & QC-level assignment matrix (per-output QC tiering) | Statistical programming QC lead | ICH E6(R3) risk-based quality management; ICH E8(R1) | QC lead sign-off; mandatory independent double-programming for RED outputs |
| S4-30 | Concentration-QTc (C-QTc) model assumption-check & QC record | Pharmacometrician / cardiac-safety statistician | ICH E14 / E14-S7B Q&A; FDA C-QTc guidance | Independent cardiac-safety statistician review |

Stage gate: All outputs QC-passed. 30 deliverables.

## S5: Reporting & CSR

Results become the CSR: statistical methods and results text, in-text tables/figures, appendices, the submission package, and cross-document consistency.

| ID | Deliverable | Owner | Standard | QC |
| --- | --- | --- | --- | --- |
| S5-01 | CSR Statistical Methods section (Section 9.7 / 11) per ICH E3 | Lead biostatistician | ICH E3 (Section 9.7/11 structure), ICH E9 + E9(R1) estimands, CDISC ADaMIG v1.3 (population/derivation traceability) | Peer review by second biostatistician against final SAP; cross-check that every method maps to a reported output; medical-writer editorial QC; SAP-vs-CSR methods reconciliation checklist |
| S5-02 | CSR Results: in-text (in-body) summary tables and figures | Stat programmer | ICH E3 (Section 10–12 Results), CDISC ADaMIG v1.3 (source datasets), Phoenix WinNonlin (NCA engine of record) | Independent double-programming or 1:1 reconciliation of every in-text value against the corresponding full TLF and source ADaM; numerical-consistency check; QC log signed off |
| S5-03 | Biostatistician contribution to and review of the CSR draft (Results text, consistency QC) | Lead biostatistician | ICH E3, ICH E9/E9(R1), 21 CFR Part 11 (review records/audit trail) | Documented number-by-number consistency check (CSR-vs-TLF-vs-ADaM); second-reviewer spot-check; tracked-changes/comment resolution log retained as a controlled record |
| S5-04 | CSR Appendix 16.1.9: Documentation of statistical methods incl. final SAP | Lead biostatistician | ICH E3 (Appendix 16.1.9), ICH E9/E9(R1), 21 CFR Part 11 / ALCOA++ (versioning, audit trail) | Completeness/version reconciliation (approved versions only); cross-check SAP content vs CSR Methods; QA review of appendix assembly |
| S5-05 | CSR Appendix 16.2: Data listings (by participant) | Stat programmer | ICH E3 (Section 16.2), CDISC SDTMIG v3.4 / ADaMIG v1.3 | Independent double-programming or QC review of each listing; reconciliation against summary TLFs; QC log |
| S5-06 | CSR appendices: Define-XML + reviewer guides (cSDRG/ADRG) and annotated CRF as submission appendices | Stat programmer | CDISC Define-XML v2.1, cSDRG/ADRG templates, CDISC Controlled Terminology, FDA/PMDA submission requirements | Pinnacle 21 conformance re-run on final datasets; reviewer-guide completeness check; define-vs-dataset consistency QC |
| S5-07 | Patient narrative data support (safety narratives) | Stat programmer | ICH E3 (Section 12.3.2 / narratives), ICH E6(R3) GCP, 21 CFR Part 11, ALCOA++ | Narrative-to-source data reconciliation per participant; independent check of the trigger list (all deaths/SAEs captured); QC log |
| S5-08 | Participant (patient) profiles | Stat programmer | ICH E3, CDISC SDTMIG v3.4 / ADaMIG v1.3, 21 CFR Part 11 | Spot-check profiles vs source listings; independent review of profile program; reconciliation against ADaM |
| S5-09 | Submission datasets + analysis programs as regulatory deliverables (with ADRG/cSDRG) | Stat programmer | CDISC SDTMIG v3.4, ADaMIG v1.3, Define-XML v2.1, Controlled Terminology; FDA Study Data Technical Conformance Guide (v6.3, Oct 2026); 21 CFR Part 11 | Final Pinnacle 21 conformance; independent double-programming evidence retained; program executability/QC review; traceability raw→SDTM→ADaM→TLF confirmed |
| S5-10 | Traceability matrix (raw → SDTM → ADaM → TLF/CSR) | Lead biostatistician | CDISC ADaMIG v1.3 (traceability), Define-XML v2.1 value-level metadata, ICH E3, 21 CFR Part 11 / ALCOA++ | Independent verification that each CSR/TLF number traces to a derivation and source; gap review; QA audit |
| S5-11 | QC of CSR-vs-TLF-vs-dataset numerical consistency | Lead biostatistician | ICH E3, ICH E9, 21 CFR Part 11 / ALCOA++ (QC records, audit trail) | Independent reviewer performs the check; discrepancy log tracked to closure; second-level QA sign-off |
| S5-12 | Statistical input to clinical study synopsis and briefing documents | Lead biostatistician | ICH E3 (synopsis), ICH E9/E9(R1), ICH M11 alignment for protocol/briefing context | Consistency check vs CSR body and TLFs (numbers identical); peer/medical review; sign-off |
| S5-13 | Statistical/biometrics sign-off and CSR release for submission | Lead biostatistician | ICH E3, ICH E6(R3) GCP, 21 CFR Part 11 / ALCOA++ (e-signatures, audit trail), CDISC submission standards | Final QA review; confirmation all discrepancy logs closed; e-signature with audit trail; engine-of-record records (software and version) attached |
| S5-14 | eCTD Module 5 submission package assembly & study-data standards conformance (study data reviewer's guide bundle, study-tagging) | Regulatory + biometrics submission lead | FDA Study Data Technical Conformance Guide; eCTD; Define-XML v2.1 | Submission-readiness review; Pinnacle 21 package validation |
| S5-15 | Analysis Data Reviewer's Guide of record finalization & cross-document consistency (SAP↔Define↔ADRG↔CSR) | Lead biostatistician + metadata lead | ICH E3; ADaMIG v1.3; Define-XML v2.1; cSDRG/ADRG | Biostatistician sign-off; documented discrepancy closure |

Stage gate: CSR draft delivered. 15 deliverables.

## CDISC dataset & metadata inventory

The standardized-data spine that makes the study submission-ready (SDTM → ADaM → Define-XML, with conformance and reviewer guides).

| ID | Deliverable | Standard | QC |
| --- | --- | --- | --- |
| S3-04 | SDTM datasets: DM (Demographics) | CDISC SDTMIG v3.4, Controlled Terminology, Define-XML v2.1 | Independent double-programming + Pinnacle 21 conformance; reconciliation to raw and randomization |
| S3-05 | SDTM datasets: PC (Pharmacokinetic Concentrations) | CDISC SDTMIG v3.4 (Findings), Define-XML v2.1, value-level metadata; CT for units/analytes | Independent double-programming + Pinnacle 21; 100% reconciliation to bioanalytical transfer (record count, value, BLQ flags); nominal-vs-actual time check |
| S3-06 | SDTM datasets: PP (Pharmacokinetic Parameters) | CDISC SDTMIG v3.4 (PP domain), CT for PK parameters (PKPARMCD), Define-XML v2.1, RELREC linkage to PC | Reconciliation to Phoenix output (the engine of record); independent double-programming of the SDTM structure; Pinnacle 21 |
| S3-07 | SDTM datasets: EX (Exposure) | CDISC SDTMIG v3.4 (Interventions), Define-XML v2.1, Controlled Terminology | Independent double-programming + Pinnacle 21; reconciliation to randomization and to PC time-after-dose derivation |
| S3-08 | SDTM datasets: AE (Adverse Events) | CDISC SDTMIG v3.4 (Events), MedDRA (versioned), Define-XML v2.1, CT | Independent double-programming + Pinnacle 21; MedDRA coding QC; reconciliation to safety database/SAE recon |
| S3-09 | SDTM datasets: LB (Laboratory) | CDISC SDTMIG v3.4 (Findings), CT/LOINC, Define-XML v2.1 value-level metadata, unit standardization | Independent double-programming + Pinnacle 21; 100% reconciliation to lab transfer; unit conversion QC |
| S3-10 | SDTM datasets: VS (Vital Signs) | CDISC SDTMIG v3.4 (Findings), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; reconciliation to raw |
| S3-11 | SDTM datasets: EG (ECG) | CDISC SDTMIG v3.4 (Findings), CT, Define-XML v2.1; time-matched to PC for C-QTc | Independent double-programming + Pinnacle 21; reconciliation to ECG core-lab transfer; PK time-matching QC |
| S3-12 | SDTM datasets: DS (Disposition) | CDISC SDTMIG v3.4 (Events), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; reconciliation to enrollment/randomization counts |
| S3-13 | SDTM datasets: MH (Medical History) | CDISC SDTMIG v3.4 (Events), MedDRA, CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; coding QC |
| S3-14 | SDTM datasets: CM (Concomitant/Prior Medications) | CDISC SDTMIG v3.4 (Interventions), WHODrug (versioned), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; coding QC |
| S3-15 | SDTM datasets: PD/DV and other supporting domains (PD/PE/SU/QS, DV, CO, SE/TA/TV/TE trial design, SUPPQUAL, RELREC) | CDISC SDTMIG v3.4 (Findings/Events/Special-Purpose/Trial-Design/SUPP/RELREC), CT, Define-XML v2.1 | Independent double-programming + Pinnacle 21; RELREC integrity check (PC<->PP); deviation-classification reconciliation |
| S3-16 | SDTM Define-XML (define.xml + stylesheet) | CDISC Define-XML v2.1, SDTMIG v3.4, Controlled Terminology | Pinnacle 21 Define conformance + dataset-define consistency; peer review; origin/aCRF cross-link check |
| S3-17 | SDTM Reviewer Guide (cSDRG) | PHUSE cSDRG template, CDISC SDTMIG v3.4, Define-XML v2.1 | Peer review; consistency with Define-XML and Pinnacle 21 explanations; sign-off |
| S3-18 | ADaM datasets: ADSL (participant-level analysis dataset) | CDISC ADaMIG v1.3, Define-XML v2.1, traceability to SDTM, CT | Independent double-programming + Pinnacle 21 ADaM checks; population-flag reconciliation to disposition/randomization |
| S3-19 | ADaM datasets: ADPC (PK Concentrations Analysis) | CDISC ADaMIG v1.3 (BDS / PK ADaM), Define-XML v2.1, traceability to PC/EX, CT | Independent double-programming + Pinnacle 21; time-after-dose & BLQ-rule QC; reconciliation to PC |
| S3-20 | ADaM datasets: ADPP (PK Parameters Analysis) | CDISC ADaMIG v1.3, Define-XML v2.1, traceability to PP/Phoenix, CT (PK params) | Reconciliation to Phoenix (engine of record); independent double-programming; Pinnacle 21 |
| S3-21 | ADaM datasets: ADAE (Adverse Events Analysis) | CDISC ADaMIG v1.3 OCCDS, MedDRA, Define-XML v2.1, traceability to AE, CT | Independent double-programming + Pinnacle 21; TRTEMFL logic QC; reconciliation to SDTM AE & SAE database |
| S3-22 | ADaM datasets: ADLB (Laboratory Analysis) | CDISC ADaMIG v1.3 BDS, Define-XML v2.1 value-level metadata, traceability to LB, CT | Independent double-programming + Pinnacle 21; baseline/change & category-derivation QC; reconciliation to LB |
| S3-23 | ADaM datasets: ADVS (Vital Signs Analysis) | CDISC ADaMIG v1.3 BDS, Define-XML v2.1, traceability to VS, CT | Independent double-programming + Pinnacle 21; baseline/change QC; reconciliation to VS |
| S3-24 | ADaM datasets: ADEG (ECG Analysis) | CDISC ADaMIG v1.3 BDS, Define-XML v2.1, traceability to EG/PC, CT; ICH E14/concentration-QTc practice | Independent double-programming + Pinnacle 21; QTc category & time-matching QC; reconciliation to EG |
| S3-25 | ADaM datasets: ADPD and other analysis datasets (ADPD, ADCM, ADMH, deviation/exposure analysis as applicable) | CDISC ADaMIG v1.3 BDS/OCCDS, Define-XML v2.1, traceability to SDTM, CT | Independent double-programming + Pinnacle 21; PK-PD linkage & baseline/change QC |
| S3-26 | ADaM Define-XML (define.xml + stylesheet) | CDISC Define-XML v2.1, ADaMIG v1.3, Controlled Terminology | Pinnacle 21 Define conformance + dataset-define consistency; derivation-method review; traceability check |
| S3-27 | ADaM Reviewer Guide (ADRG) | PHUSE ADRG template, CDISC ADaMIG v1.3, Define-XML v2.1 | Peer review; consistency with Define-XML, SAP and Pinnacle 21 explanations; sign-off |
| S3-28 | CDISC conformance / validation (Pinnacle 21) report: SDTM & ADaM | CDISC conformance rules, SDTMIG v3.4, ADaMIG v1.3, Define-XML v2.1, FDA/PMDA validator rules | Validated Pinnacle 21 engine; documented triage/disposition of every finding; reviewer-guide reconciliation |
| S3-31 | Dry-run / test datasets & dry-run TLF execution | Sponsor validation/QC plan; CDISC SDTMIG v3.4/ADaMIG v1.3; 21 CFR Part 11 (program version control) | Independent double-programming on dry-run; shell-vs-output reconciliation; defect tracking to closure |
| S3-34 | Traceability (raw -> SDTM -> ADaM) matrix | CDISC SDTMIG v3.4/ADaMIG v1.3/Define-XML v2.1 traceability principles; ICH E6(R3), ALCOA++ | Cross-link verification raw<->SDTM<->ADaM; peer review; consistency with define/reviewer guides |
| S3-35 | Controlled Terminology & coding-dictionary version management (CDISC CT, MedDRA, WHODrug) | CDISC Controlled Terminology (versioned), MedDRA, WHODrug; Define-XML v2.1; 21 CFR Part 11 | Version-lock verification; CT-conformance via Pinnacle 21; coding QC against locked dictionaries |
| S3-42 | PK sampling-time deviation & actual-vs-nominal time reconciliation (PK timing dataset QC) | CDISC PC/PP domains; FDA PK guidance; ALCOA++ | Independent check vs source; PK scientist sign-off |

## TLF & analysis-output inventory (Stage 4)

Tables, listings, and figures by domain, plus the PK/PD analyses. Reported numbers come from validated programs and engines and are independently double-programmed.

| ID | Deliverable | Owner | QC |
| --- | --- | --- | --- |
| S4-02 | Disposition tables (screening, randomization, dosed, completed/discontinued; analysis-set attribution) | Stat programmer | Independent double-programming + reconciliation against shells; population counts cross-checked to ADSL |
| S4-03 | Demographics & baseline characteristics tables | Stat programmer | Independent double-programming + reconciliation; descriptive stats verified against ADSL/raw |
| S4-04 | Exposure / dosing & treatment-compliance tables | Stat programmer | Independent double-programming + reconciliation; dosing records cross-checked to EX/EC |
| S4-05 | Protocol-deviation summary tables (with importance classification) | Stat programmer | Independent double-programming + reconciliation; classification reviewed at blinded data review |
| S4-06 | PK concentration summary tables + mean concentration-time figures (linear & semi-log) | Stat programmer | Independent double-programming + reconciliation; BLQ handling verified; figures QC'd vs tables |
| S4-07 | NCA execution in validated Phoenix WinNonlin (PK parameter derivation) | PK scientist | Phoenix is the validated engine of record; independent re-derivation of key parameters (second analyst / second tool) + reconciliation; lambda_z selection reviewed; run records archived |
| S4-08 | PK parameter (NCA) summary tables (Cmax, Tmax, AUC, t1/2, CL/F, Vz/F) | Stat programmer | Independent double-programming of the summary table + reconciliation; values traceable to validated Phoenix ADPP |
| S4-09 | Dose-proportionality & accumulation analyses | Stat programmer | Independent double-programming + reconciliation; model specification reviewed; outputs traced to validated ADPP |
| S4-11 | Concentration-QTc (C-QTc) / QT-QTc analysis, if applicable | Pharmacometrician | Independent re-modeling / double-programming + reconciliation; C-QTc model assumptions reviewed; run records archived |
| S4-12 | popPK / exposure-response modeling (NONMEM/Monolix) with run records | Pharmacometrician | Run records (control streams/seeds/logs) archived; independent review of model code & assumptions; key results reproduced; VPC/GOF reviewed |
| S4-13 | Safety TLFs: TEAEs (overview, by SOC/PT, severity, relationship, by dose) | Stat programmer | Independent double-programming + reconciliation; TEAE flag/derivation verified; counts cross-checked to ADAE |
| S4-14 | Safety TLFs: deaths, SAEs, and AEs leading to discontinuation | Stat programmer | Independent double-programming + reconciliation; SAE/death flags reconciled with safety database/PV |
| S4-15 | Safety TLFs: clinical laboratory analyses (summary, change-from-baseline, shift tables, outliers, Hy's law) | Stat programmer | Independent double-programming + reconciliation; reference-range/grade derivations verified |
| S4-16 | Safety TLFs: vital signs, ECG (12-lead parameters), physical exam | Stat programmer | Independent double-programming + reconciliation; baseline/CFB and outlier criteria verified |
| S4-18 | Immunogenicity / anti-drug antibody (ADA) analyses, if applicable | Stat programmer | Independent double-programming + reconciliation; TE-ADA derivation verified |
| S4-22 | TLF validation / QC documentation & discrepancy log | Stat programmer | Completeness/consistency review of QC records; lead biostatistician sign-off |
| S4-25 | Pharmacometrics / popPK analysis report | Pharmacometrician | Independent review of model & report; key results reproduced; run-record completeness check |
| S4-27 | Phoenix WinNonlin NCA parameter-derivation QC / independent NCA verification record | PK scientist + independent PK QC reviewer | Independent PK reviewer; documented parameter verification |
| S4-28 | Pharmacometrics model qualification & validation records (covariate selection, GOF, VPC, bootstrap, run log) | Pharmacometrician + independent reviewer | Independent pharmacometrics review; reproducible run records |
| S4-30 | Concentration-QTc (C-QTc) model assumption-check & QC record | Pharmacometrician / cardiac-safety statistician | Independent cardiac-safety statistician review |

## Validation & quality (cross-cutting)

- Independent double programming of every submission-grade output, with every discrepancy logged and resolved.

- Engine of record for every deliverable: reported numbers come from validated, double-programmed SAS/R programs on ADaM; NCA from Phoenix WinNonlin (version per the ADRG, currently 8.8) or PKNCA; CDISC conformance is checked with Pinnacle 21 (FDA engine 2304.3). Software version and build are documented, as FDA's statistical software statement asks.

- Data integrity: records that are attributable, legible, contemporaneous, original, accurate, complete, secure, and reliable (ICH E6(R3)); audit trails and e-signatures in systems designed to meet 21 CFR Part 11.

- Software / environment qualification (IQ/OQ/PQ) for SAS/R, Phoenix WinNonlin, NONMEM/Monolix, and Pinnacle 21.

- Named sign-off: a qualified statistician reviews and signs each deliverable.

## Appendix: AI-use proposal

A proposal, not an adopted policy, for where AI tools could assist on these deliverables and where they may not. For context, FDA's guidance on using AI to support regulatory decision-making for drugs is still a draft (January 2025), and the FDA-EMA guiding principles for AI in drug development (January 2026) are non-binding.

1. Every reported number comes from a validated program or engine. An AI tool may draft code that is one side of independent double programming, never both sides.

2. Participant-level, unblinded, or identifiable data stays inside the validated environment (a local, version-pinned model, if any model is used). Only de-identified text and specifications may go to a contracted cloud service under a data-processing agreement, never a consumer account.

3. A named statistician reviews and signs every output, and AI use is recorded.

| Tier | Deliverables | What an AI tool may do |
| --- | --- | --- |
| Green | 44 | Draft text, scaffolds, and documentation from de-identified content |
| Amber | 54 | Draft dataset or TLF code as one side of double programming |
| Red | 34 | Nothing: validated programs and engines produce the numbers, and a human checks them |

If AI tools are used, four records are kept:

- AI-01 AI-use plan: data classification and tool routing (Stage 2, before any AI-assisted work): Per planned deliverable: the data-sensitivity class and where any AI assistance may run. Participant-level, unblinded or identifiable data: a local, version-pinned model with no data leaving the validated environment. De-identified text and specifications: a contracted cloud service under a data-processing agreement, never a consumer account. Reported numbers: validated programs and engines only.

- AI-02 AI-use log (data stage) (Stage 3, kept current): Per Stage 3 deliverable: the data class, where AI assistance ran, the engine of record for any dataset, and the model version used.

- AI-03 AI-use log (analysis stage) (Stage 4, per output): Per output: the data class, where AI assistance ran, the engine of record for reported numbers (for example Phoenix WinNonlin, PKNCA or NONMEM), the model version, and retained prompts and outputs for AI-drafted code that was one side of double programming.

- AI-04 AI-use summary for the study file (Stage 5, before release): One summary across the study: model versions, the engine-of-record register showing every reported number came from a validated program or engine, and the retained prompt and output records.

The tier and AI note for each deliverable are on the spreadsheet's "AI use (proposal)" sheet.